## Sheet1
Project Plan
Start Date: | Wk 1 21/05 | Wk 2 28/05 | Wk 3 04/06 | Wk 4 11/06 | Wk 5 18/06 | Wk 6 25/06 | Wk 7 02/07 | Wk 8 09/07 | Wk 9 16/07 | Wk 10 23/07 | Wk 11 30/07 | Wk 12 6/08 | Wk 13 13/08 | Wk 14 20/08 | Wk 15 27/08 | Wk 16 03/09 | Wk 17 10/09 | Wk 18 17/09 | Wk 19 24/09 | Wk 20 01/10 | Wk 21 08/10 | Resources
Part 1 - Plan
Research Project Management Tools | Completed | [20 empty] | Internet
Create plan of project milestones | Completed | [20 empty] | Microsoft Excel
Confirm final design | Completed | [20 empty] | Figma
Part 2 - Develop
Identify and Decompose Components |  |  |  | Completed | [17 empty] | Microsoft Work
Create version 1 |  |  |  | Completed | [17 empty] | Python/VsCode
Undertake Trialling Phase 1 |  |  |  |  | Completed | [16 empty] | Microsoft Word
Undertake Testing Phase 1 | [15 empty] | Completed | [5 empty] | Microsoft Word
Reflect on Relevant Implications | [15 empty] | Completed | [5 empty] | Microsoft Word
Reflect on Process | [15 empty] | Completed | [5 empty] | Microsoft Word
Create version 2 | [6 empty] | Completed | [14 empty] | Python/VsCode
Undertake Trialling Phase 2 | [17 empty] | Completed |  |  |  | Microsoft Word
Undertake Testing Phase 2 | [17 empty] | Completed |  |  |  | Microsoft Word
Reflect on Relevant Implications | [17 empty] | Completed |  |  |  | Microsoft Word
Reflect on Process | [17 empty] | Completed |  |  |  | Microsoft Word
Create version 3 | [19 empty] | Completed |  | Python/VsCode
Undertake Trialling Phase 3 | [19 empty] | Completed |  | Microsoft Word
Undertake Testing Phase 3 | [19 empty] | Completed |  | Microsoft Word
Reflect on Relevant Implications | [21 empty] | Microsoft Word
Reflect on Process | [21 empty] | Microsoft Word
Final reflections/analysis | [21 empty] | Microsoft Word